## Mandy's list
Most links in this spreadsheet are to documents saved here: Teams / ITS816 Time Management /General / Outstanding issues - emails and documents
Time Management - outstanding tasks
ID. | Policy | Added by | Topic | Description | Priority | Action needed | Status | Owner | Possible POG item? | Relevant info | Latest position | Notes | Needs to be addressed in roll out
3 | Process | MZ | Classic and UAS | Classics and data services, and UAS departments and UAS HR. Work out the model for who does what and the corresponding access. | Low | Clearly documented guidance on who does what. Ensure all parties have the knowledge and skills to do their tasks. Ensure access matches their needs as closely as the system allows. | Closed |  | No |  | 25.04.22 Document detailing agreed split of responsiblities shared by email with Jayne Snaith, Jasmine Doris and Lois. MZ also shared doc with Jonathan Roger for ref. 07.04 Mandy to finalise document and add to Teams. 21.10. Lyndsey to support AK in updating Data Services forms. MZ to arrange to meet Jasmine in UAS HR. 09.02.21 MZ has drawn up a proposed split of resonsibilities for UAS departments. Currently being considered by Jasmine Doris and Michelle Rice. DS will remain as is for now.
s | Config | MZ | Rollover of calendar at year end | Rollover and weekly calendar. System rollover can't happen until the week in which the leave year ends. This means that staff can't see their current year balance from 1 Oct and HR staff can't start adding carry over until after the rollover has happened. | Medium | Ideally need AG to address this with new configuration. | Closed |  | No | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Useful%20emails/Core%20Time%20Calendar.msg | 09.02.22 MZ to hand over to SB. 17.01.23 - no action at this stage. | 02.11 - look at the emailabout the four staff who had a -0.5 balance. Understand what caused this for next year. | No
27 | Guidance | MZ | Amending work schedules | Work schedule amendment issue - unable to update the defaulted work schedule of new appointments in Portal. | High | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Outstanding%20issues%20-%20emails%20and%20documents/RE%20Back%20office%20sickness%20approval%20issues.msg | Closed |  | No | Task# 50458468 for Incident# 11156325 | March 2022 - Mandy emailed pilot depts. to confirm that they can now backdate work schedules. 24.11.21 - we will turn on allowing historical work schedule amendment and also switch on another menu issue. In project they had issues with this which we can't replicate. If we switch this on, it gives an option for "add personal override" but this then has no content. We have asked AG what this bit is. Overall, we think this is achievable but we need to look at updating guidance. MZ to talk to Anna about who best to take this forward. Co-ordinate the system change with the updated guidance and comms. Change ref: 20013454 09.02.22 Hand over to Tonya/Julie/Michelle. 16.03. Requested MOS make the manu profile updates needed. I will then email the pilot users to let them know.
29 | Config | MZ | Recording absence in BO | Non-pilot departments who use CoreTime can no longer record sickness absence in the back office. | High | See description and email link. Currently with Access Group. | Closed |  | No | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Outstanding%20issues%20-%20emails%20and%20documents/RE%20Back%20office%20sickness%20approval%20issues.msg | May 2022 Lois has contacted all Absence Administrators to ask who still needs BO access and is updating the list to share. 26.04.22 MZ emailed Anna to ask for the latest on this as got no reply to previous email dated 22.10.21. 2.11. SW - The jira is UOTA-251 and it is with Richard to check that removing default shift pattern from a workgroup doesn’t have a negative impact. 17.01.23 - Agreed no further action - absence is recorded in portal. |  | No
31 | Guidance | MZ | Data items reference document | Incorporate new data items (e.g. clinical grades) into the relevant How To Guide. | Medium | The How To Guide currently only includes information relevant to staff on grades 1-10. Need to update this to include clinical grades and any others. Might be best as a table in an appendix. Likely to have more information added as we roll out. Also consider where we hold the data relating to TUPEs (see link in Notes - contains personal data, MZ and SB know password). | In progress |  |  | https://teams.microsoft.com/_#/school/files/NDM%20annual%20leave%20rollout?threadId=19%3Aae6f79c2de95467fb90a65456d3a92c4%40thread.tacv2&ctx=channel&context=NDM%2520annual%2520leave%2520rollout&rootfolder=%252Fsites%252FUniversityAdministrationandServices | 7.04.22: This has been handed to Julie and Michelle for action. 22.10. NDM have access to the TUPE and Clinical spreadsheet in Teams but we need a longer term solution. 17.01.23 - Page 3 of https://hrsystems.admin.ox.ac.uk/files/how-toguide-assignabalancepdf. We will need to review what is avaialble to HR Admins to help them asssign balances correctly as we roll out further. We can't continue to publish all of the balances and holiday schemes in the 'Assign Balance' how to guide as we roll out. Due to length of the list. There is a depenency on how we roll out, for example, we could attempt to group together similar departments to make set up and maintencnace efficient and manageable. The blocker here is that fixed closure dates vary across depts and are deicded locally and a different times of the year. This needs to flag to HR Director as an example of varying practices across the devloved structure causing significant impact on efficient processes and set up. | Clinical data will be relevant to other Med Sci departments when we rollout. | Yes
35 | Guidance | MZ | Co-workers and team calendar | There was initially some confusion over the different configuration for NDM and the rest of the pilot when it comes to the team and co-workers calendars. Simon and Michael have now got to the bottom of this and the guidance needs updating. | Medium | NDM have no visibility at all of any calendars or the team scheduler. The rest of the pilot have no visibility of the calendars but managers can look at the Team Scheduler in the Workforce Management area before approving leave requests, which essentially serves the same purpose. Need to update both sets of guidance to accurately reflect what's available in the system. |  |  |  | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Outstanding%20issues%20-%20emails%20and%20documents/Calendars%20and%20scheduler%20-%20Simon's%20email.msg | 7.04.22 How-To guides need reviewing to ensure this is reflected. 24.11 we will rely on team scheduler (as per current config in Live - check and update guidance) but NDM don't have access to this. 17.01.23 - (1) page 2 of https://staff.admin.ox.ac.uk/files/how-toguide-approveleaverequestspdf The option to select 'Cooworkers leave / absence' option is not available and reference should be removed. The process for navigating to WFM dashboard and selecting team scheduler, in order to check their team's absence should be added to the guide. (2) A secondary issue sits behind this which will need to be looked at again when we have removed the default work group. The issue is that managers with multiple appointments may end up seeing data for staff who have the default work group assigned. Which will include pensioner records. As NDM managers do not have access to the Team Scheduler within the Workforce Management dashboard, because they are not allowed to see sickness absence records, they have no way of accessing their team's annual leave records. When the default work group has been removed, we should be able to reinstate the process of navigating via cooworkers leave / absence. We will need to reenable 'coreportal - calendar - time' against the menu profile 'coreportal_manager_timesheet' | 25.11 Double check with AG that no option at all to see the Team Scheduler withou drilling into the absence details. 30.11 MZ emailed JL to get her view on this.
39 | Guidance | MZ | Split funding | Casual appointments cannot have split funding between GL cost centres and Project codes. Only options are to journal downstream or create separate appointments. Separate appointments are only appropriate if each represents a separate casual role with its own Letter of Engagement. Otherwise it must be done via journalling. | Medium | Update the relevant How-To guide.Create an internal knowledge document explaining why this approach is necessary in system terms. | In progress |  |  |  | 7.04.22: Document with Julie for How-To guide update. 11.02.22 Draft of internal knowledge document compete. Waiting on Alison's feedback then will circulate to those who attended the meeting. Once agreed, will hand over to Julie for guidance updates. 17.01.23 - Add info from the FAQ to the https://hrsystems.admin.ox.ac.uk/files/scenariofactsheet-enablecasualworkertosubmittimesheetviahrself-servicepdf factsheet - last page.
1 | Config | MZ | FTE hours | Historical confusion over the full time hours on the appointment for clinical grades. Some are set at 37.5 hpw others on 40hpw. | Low | Need to ensure all clinical appointments in People Management hold the correct full-time hours and that these match the set up in Time Management. Consider impact of any corrections on salary and allowances. Needs thorough investigation followed by correcting of the records. | Closed |  | No | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem-NDMannualleaverollout/_layouts/15/Doc.aspx?OR=teams&action=edit&sourcedoc={F6947BE9-9120-4E0F-ACB4-E2965BD0DC54} | 19.10 - Simon testing 12 different scenarios. Looks good so far. Then need to agree approach for updating the NDM records. Also check working hours for other clinical grades. Sarah R confirmed use effective date of 1 Aug 21 for any changes. 17.01.22 MZ emailed NDM HR with instructions on how to update the FTE hours and the implications. https://unioxfordnexus.sharepoint.com/:u:/r/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Outstanding%20issues%20-%20emails%20and%20documents/Clinical%20staff%20FTE%20hours.msg?csf=1&web=1&e=HfTbvO 20.01.22 MZ met with NDM HR and Gillian Morris. Gillian wants to look at contracts of impacted staff before taking any actions in the system. It is now with them to address this and nothing further we need to do.
2 | Guidance | MZ | PPCG | There are two PPCGs in the system for full time Grades 1-5. One with a shorter Friday and the other with the same length days throughout the week. I don’t think the guidance covers this. There is nothing in the Staff Handbook or contract templates about this but we know there is some custom and practice for a shorter Friday for these grades. I believe that if the shorter Friday option is selected, the Balance should be in Hours. But check with Simon or Michael. | Low | Update the relevant guidance to explain that there is a choice of support staff PPCG. If no preference, advise go for the one with five equal length days. | Not started |  |  |  | 7.04: Needs investigating before guidance updated. Do these staff need to book leave in hours rather than days (or does the system know that a Friday is less)? Alternative is that the shorter Friday isn't offered in the system.
4 | Reports | MZ | PERDEP01 | PERDEP01 CoreTime report produces different results if you enter dept code and/or department. | Low | Investigate the root cause of this issue. Are the departments entering the hierarchy information differently? If so, identify incorrect records and advise the department. Consider guidance and comms on hierrachy info. Or, is it a report issue? | Not started |  | No |  | Mandy has sent this to Athena to investigate.
5 | Process | MZ | Substantive appointment | Substantive appointment issue - process for unapproved timesheets and long term plan. This also impacts depts using leave and absence. | High | A number of us met on 28 July to look at workarounds for this and agree the best approach. I can't find a record of what was agreed. Think it was that the Helpdesk would approve unapproved timesheets for non-susbtantive appointments in the short-term but what about the long term? Do we have an open JIRA? What other processes does this issue affect? See additional link in notes for a summary of the issues and Mandy's and Simon's comments (made before the meeting took place). | In progress |  | No | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Useful%20emails/RE%20CoreTime%20-%20Substantive%20Appt%20Issue.msg | March 2022: Widget released to departments. 09.02.22 Widget being tested. Not a long term solution because it has no security applied to it. Need to continue working on howe we address this before wider rollout. Also needs a filter column which we have fed back to AG. | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/_layouts/15/Doc.aspx?OR=teams&action=edit&sourcedoc={7419D75F-331A-427E-9E66-7BC4BF6C4B7B}
6 | Policy | MZ | Disability leave | Disability related leave - email from Karina | Low | Look at the email chain and understand the potential issues around disability leave. Gather requirements from EDU and Policy team and decide on system configuration and associated process. Update guidance accordingly. | Not started | Lois | No | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Outstanding%20issues%20-%20emails%20and%20documents/FW%20Disability-related%20leave.msg | 09.02. Low priority. MZ to dicuss with Tonya and agree whether we will bother taking this forward or wait for further contact from EDU.
7 | Reports | MZ | BAU processes | Identifying new starters in scope. | High | Ensure that Michael has a report/process for new starters that need relevant Time menu profiles added and for removing those who move to out of scope appointments. Complex because not all employees in any given department are in scope. | Closed | SB | No |  | 09.02 MZ will hand over to Simon. Think about the new dept code example that we had for NDM.
8 | Config | MZ | Parental leave | Why isn't parental leave an option in the Support Staff PPCG? | Low | Understand why Parental Leave isn’t an option to record for Support Staff. Was this intentional or an oversight? | In progress | SB |  | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Outstanding%20issues%20-%20emails%20and%20documents/RE%20Parental%20leave.msg |  | 09.11 TH confirmed that staff should not be able to book unpaid parental leave and including this on the AR PPCG was a config error. Simon to update the PPDG config so that none of them allow staff to book parental leave (only HR Admins)
9 | Process | MZ | BAU processes | Ensure yearly tasks are all documented and well understood. See email from Simon. Remember that we need to remind them to do their manual balance adjustments, provide annual/TTO work schedules for us to upload (then they assign) and provide their calendars of fixed closure days etc (including for TUPEs). See Tony's work so far. Note - second link to useful email in Notes column. Make sure that when requesting the new calendar details we explicitly ask for the number of floating days as well as fixed days and BH. Then build in a check to ensure the total comes to what we would expect. | Medium | As per description | In progress |  |  | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Outstanding%20issues%20-%20emails%20and%20documents/Time%20Management%20information.msg | May 22: Lois producing end of year checklists, templates for gathering dept. info. and draft email to send to depts. This will include an invitation to a training session to go through items on checklist. 09.02 MZ will hand over to Simon. | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Outstanding%20issues%20-%20emails%20and%20documents/FW%20Time%20Project%20-%20System%20maintenance%20document%20handover.ms
10 | Policy | MZ | Bank holiday and closure day discrepancy | Mismatch between how Policy team calculator and system apply entitlement for bank holidays and closure days for part-years. System allocates those days that fall in the part-period, Policy team calculator gives exact pro-rata amount. | High | Convince AG to update their config to allow BH and closure days to be allocated on a strictly pro-rata basis for part-year contracts. The alternative is to either manually adjust every balance (not sustainable) or change our way of allocating BH and fixed day entitlement in these circumstances (not palatable as likely to represent a change in Ts and Cs if challenged). | Not started |  | No | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Outstanding%20issues%20-%20emails%20and%20documents/JIRA%20UOTA-199%20-%20holiday%20calc%20anomaly.htm | 02.11. MZ meeting Policy Team on 9.11 to discuss. LC raised with AG in an email on 26.10: https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Outstanding%20issues%20-%20emails%20and%20documents/RE%20#External#%20Pro-rata%20calculation%20of%20BH%20and%20Closure%20days.msg 09.11MZ met with Ruth and Kate. No desire to go down the contractual change route. Need a system solution. MZ to make Lou and Jenny aware. 09.02 Lyndsey Middleton will do some work to look at the impact of living with this disparity. Numbers affacted, frequency, difference in hours/days allocated. With a view to making a pragmatic decision. Possibly take to HRSSC for sign off? | Note that the JIRA is closed.
11 | Policy | MZ | Long service leave | Long service leave. There is no clear policy on whether long service leave should be applied in the year in which the anniversary is reached or in the year following the anniversary (or possibly pro-rata but this seems unnecesarily complex). The system can be configured as we wish. It is currently configured to apply it in the leave year following the anniversary as this matched the off-system calculator for 20/21. However, the off-system calculator for 21/22 applies it in the year of the anniversary! NDM want it to be set to following year, UAS HR want it in the year. Can configure per balance but this would ass complexity. Ideally want a clear University-wide policy. | Medium | Need a decision on approach and to configure the system accordingly. Need to consult HR Admins in departments (and possibly more widely). Need to consider how to manage claims for backdated leave if applicable. | In progress |  | No |  | 9.11 MZ met with Ruth and Kate. Agreed that LSL should be applied in the leave year in which the anniversary is reached. Kate to update webpage and calculator with a note to this effect and communicate at nex briefing. MZ to communicate to pilot depts and liase with SB to update system. MZ to share this decision with NDM and to discuss the impact and timescale. 09.02 At the last meeting with NDM we felt that making the change from the next leave year would be sensible. They are happy to do that provided that they have confirmation from us. MZ emailed SB to ask if we could future date this config change in the system. If so, MZ to communicate this future change to pilot departments now. 11.02.22 MZ replied to SB's email in which he outlined options and suggested we go for this approach: • We could put off making the change until we rolled over to the new leave year (2022-23) which hopefully would mean it would not back date the adjustments to the current year (2021-22) and would therefore take effect against each balance that the LOS was attached to.
12 | Process | MZ | Departmental processes | Ensure pilot departments have established internal processes for keeping work groups, managers, work patterns up to date. | High | Contact pilot departments to ensure they have processes in place to maintain data relevant to Time Management. Supplement with regular Bulletin items (add to schedule). | Closed |  | No
14 | Process | MZ | BAU processes | Ensure that we have a workable process for identifying which work groups new Absence Administrators need access to. | High | As per description |  |  | No |  | 09.02 MZ to hand over to SB
15 | Guidance | MZ | Carry over of leave | There is different practice when it comes to carry-over of annual leave. This means that we can't automate the process of carry over and it needs to be done manually at the end of each leav year which is very laborious. | Medium | Explore with key users/POG/Check and Test group what their desired outcome would be. Flag with Policy Team the benefits of a University-wide policy on whether carried over leave needs to be taken within 3 months. | In progress |  | Yes but not yet |  | 9.11 MZ met with Kate and Ruth. They support having a consistent,communicated approach. Kate to do some research (as she thought we already had a policy) and come back to me. Simon's testing suggests it might not work! Consider seperating out the fucntionality from the policy aspect. 11.02.22 Assurance Directorate are of the same view as NDM, they do not want automated carry over of leave. So my current view is that we should keep this switched off and departments manually add carried over leave once this has been approved off system. The HR Support website has been updated to say that leave carried over should be taken within three months - i.e. by 31 December. But UAS HR and Assurance did not apply that last year. My view is that our guidance should direct them towards using the "Carried Over" functionality but state that exceptionally leave could be added to the main balance. Might be helpful to have a check list of annual leave year-end activities that includes communications to departments about what they need to do and the timeframes for this. See also item 9. | NDM - not necessarily desirable to automate carry-over. Once they have some data, this wil help inform the decision on best approach.
16 | Reports | MZ | Report to show balances | Does the report that shows balances have the ability to show the current, previous and future period? This would be really useful for checking balances around leave year-end. | Medium | Develop and release a report to HR Admins that shows the balance for each employee at the end of the previous leave year(s). | Closed |  | No - NDM feedback will suffice |  | March: Report made live. Lois to notify depts. 16.10. Simon has written this and the code is saved in the Functional Analyst SQL Depository as “Core Time Balance History per Employee” . Needs to be developed and released to HR Admins. 08.11 MZ gave SB some feedback on the report. 17.11 MZ gave SB some further feedback on the revised version of the report. 29.11 MZ emailed to NDM and asked for their feedback. 09.02.22 MS has chased NDM a few times. Hand over to Tonya.
17 | Guidance | MZ | Rejecting leave | Ensure relevant guide explains what to do if a manager wants to reject a request they have previously approved (think employee has to cancel it). | Low | Update relevant How To guide and any internal knowledge base | Not started
18 | Guidance | MZ | Non-employee managers | Non-emps approving leave/acting as work group manager. They will be ssigned just the manager dashboard and org roles. | Low | Ensure that this decision is documented and included in How-To Guide | Not started
19 | Guidance | MZ | Correcting a balance type | Need guidance on what to do if you need to correct or amend a balance type. | Low | Update the relevant How-To Guide to reflect the following advice: "Yes, if an incorrect balance is assigned, or assigned with the incorrect unit, it should be deleted and reassigned. Removing the balance does not impact any leave requests, those should still be deducted from the new balance, but I believe it will remove any manual balance adjustments, so if there are any these would need to be recreated." | Not started
20 | Guidance | MZ | Balances screen | Balances screen is confusing where employee has multiple appointments. Regardless of which appointment is selected in the drop down at the very top of the screen, it shows all balances assigned to all appointments. You need to click into the relevant balance for it to show the corresponding Transactions below. | Low | Consider updating the guidance for HR staff. Look at TERESA STREET (2019098) example. | Not started
21 | Guidance | MZ | Multiple work group managers | Build into onboarding process, supplying departments with multiple manager reports and giving explicit guidance on this. | Low | Transfer this item to Lyndsey's onboarding task list, then delete this item from here. | Closed
22 | Reports | MZ | PERDEP16 | NDM have requested that a filter for employee status is added to PERDEP16. | Low | Add the filter to the report and republish | Closed | MZ |  |  | 09.11 Updated report with new parameter released. To be communicated in November Bulletin.
23 | Guidance | MZ | Approver roles | Visual of approver roles. Aim for this replace numerous FAQs on this. | Low | Aim for a matrix that shows the different manager/approver roles and what it allows them to do. To be useful to us and end users. Publish this on the Staff Gateway page as well as our pages. Current FAQs on the SG page on this are very confusing so try and built the content of those into this matrix. | In progress | LM |  |  | 22.10 - Lois has done a very basic visual. Mandy needs to go through this with her and involve Michael to come up with something more comprehensive and detailed, while remaining user-friendly.
24 | Guidance | MZ | Standard hours | Essential that "standard" hours field on the Appointment is completed. If left blank, the balance won't generate. | Low | Update relevant How To guide and any internal knowledge base | Closed |  |  |  | 16.02. - Field is about to be made mandatory so no need to action this.
25 | Config | MZ | Standard hours | Configuration of balances - might be the option to based them on the FTE not the FTE hours which could be simpler and mean that the standard hours field is not essential. | Low | Analysts to explore and test options and decide whether we want to retain current config or make a change. | Not started |  | Yes | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Useful%20emails/Balance%20config%20re%20standard%20hours.msg | 09.02.22 Hand over to Simon
26 | Process | MZ | Default work group | Removal of the Default Work Group will allow us to switch on the team shared calendar function | Low | Change guidance on work groups, ensure all staff, including casuals, are in a valid work group. Remove the default work group as an option. This is a very big piece of work and arguably should be left until rollout is complete. | Not started |  | Yes |  | 09.02.22 Hand over to TIK for POG list
28 | Config | MZ | Multiple appointments | Multiple appointments - looking at incorrect holiday scheme. Where an employee holds two appointments, substantive appointment in scope and non-substantive out of scope, the system is looking at the calendar on the substantive appointment when calculating the balance, which can result in errors (Paul Tappin) | High | Keep chasing AG! | In progress | LM | No | UOTA-252 | 01.11. Logged with AG as a bug and assigned to their development team. They are going to come back to us later this week with an estimated fix date. 09.02.22 Assume project will hand over to BAU if not fixed by project closure. 09.02.22 LM confirmed 'Nick has chased dev again today and Nick will speak to the product manager to escalate.'
30 | Guidance | MZ | Self-managed leave | Self-managed leave is one of the PPCG options. Reflect this in the guidance. |  | Understand what Self-Managed leave allows in terms of system use and update the How To Guide and internal knowledge base accordingly. | Not started |  |  | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Outstanding%20issues%20-%20emails%20and%20documents/RE%20Quick%20Q%20-%20self-managed%20leave.msg |  | This is what Tom advised and I relayed to NDM: I have had the following response from the project team in response to the question about what “self-managed leave” provides: • The employee would be able to see their balance, but they would not be able to record leave against it. • Sickness should not be impacted: An HR Admin can still record absences against the record, including sickness absence. If the sickness absence is returned to the employee, they should still be able to self-certify. It’s a shame that they can’t record their own leave against their entitlement (in the event that they want to track it).
32 | Config | MZ | Out of scope config | Understand what needs to be done where employees have multiple appointments, where one is in scope and others aren't. How criticial is it to have an "out of scope" PPCG on the other appointment? What does this drive? What about out of scope work group config? | High | See description | Not started |  | No | https://unioxfordnexus.sharepoint.com/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Outstanding%20issues%20-%20emails%20and%20documents/Time%20-%20Out-of-scope%20workgroup%20configuration.msg
33 | Guidance | MZ | Leaver process | Document this in guidance, all implications. Including Transfers out. | [6 empty] | 04.11. SB asked MOS to document transfer process
34 | Config | MZ | Rounding | For part-time staff, the system rounds up their balance to the nearest half hour which is logical. However, for full-timers who work for part f the leave year and have their balance in days, the system does not apply any rounding. We would like it to round up the balance to the nearest half day. | Medium | AG to advise whether the system configuration exists to support this - if it does, we need to configure, test and make the change. If it doesn't, raise it on their ideas portal. | Closed | SB |  |  | 29.11. Change released into Live today. Email went to Pilots on Friday 26.11. Might want to make sure the guidance reflects this. Line added re guidance so this item can be closed.
36 | Process | MZ | Authorising manager access | Guardian could act as a blocker for approving manager changes. Need to agree a practical approach to support delegation of approval to HR staff. | Low | Agree and communicate a process. E.g. will we keep a list of authorised approvers? Would we allow anyone with Personnel Admin role to do it? | Not started |  | Yes but not until more departments on board |  |  | Have agreed informally in NDM for Elena to delegate authority to Lois and Sarah.
37 | Config | MZ | Email notifications | Automated emails for approving leave - any chance of a follow up email to remind managers. |  |  | In progress |  | No | Incident number 11169055 | 09.02.22 HC thinks this doesn't seem possible but has raised with AG. 28.02.22 HC confirmed AG have said not possible. TIC to raise on Ideas Portal?
38 | Guidance | MZ | Rounding | For part-time staff, the system rounds up their balance to the nearest half hour. For full-timers who work for part of the leave year and have their balance in days, the system rounds up to the nearest half day. Need to ensure guidance reflects this. | Medium | Decide which guides need updating with this information. Probably guides for staff and also HR guide(s). May want to update internal knowledge base (whatever that is!) with my chat message from Simon (see relevant info). |  |  |  | https://teams.microsoft.com/l/file/D18BF124-4213-42F9-9685-95132C504484?tenantId=cc95de1b-97f5-4f93-b4ba-fe68b852cf91&fileType=docx&objectUrl=https%3A%2F%2Funioxfordnexus.sharepoint.com%2Fsites%2FUniversityAdministrationandServices-ITS816-CoreHRTimeManage
40 | Guidance | MZ | TOIL | TOIL is only available as an option for Support Staff grades. It would be helpful if the guides specified this. It would also be helpful to understand what happens in the system when someone requests TOIL. Does it take the time out of the leave balance? If so, it's really important that a manual balance adjustment has been done to credit the leave balance with the TOIL hours worked. If it does nothing to the balance then the amount of TOIL accrued would need to be tracked off system. |  | Update guides | Not started |  | No
41 | Guidance | MZ | Recording absence | CS has been running TIMDEP03 and the results indicate that managers/employees are often creating a separate record for every day of absence instead of one record to cover the whole period. Perhaps they don't understand that the system knows when weekends etc are. |  | Update relevant How To guides to make it explicit that you only need one record for each continuous period of absence (even if it spans a weekend or other non-working day. | Not started
42 | Guidance | MZ | NDM access and calendar | NDM have different access roles as they don't want line managers handling or seeing sickness absence data. Make sure the different access and the impact on their user experience is understood by the team and documented (e.g. no access to the team scheduler). |  | See description. I think this probably exists from Tom - a seem to recall a PPT slide. Ideally we would get something in a format to share with NDM so they understand.
43 | Guidance | MZ | Delegation | There are different options for delegation but the website is not very clear. |  | Update the website guidance to be really clear about what delegation options exist, how they differ, and how you set them up. Perhaps also email pilot departments with this information.
44 | Process | MZ | Mailing list | Set up a mailing list for Portal Time Management users |  |  | Not started
45 | Config | LM | Approver roles | Simon thought it might not be possible to split the roles out. Currently NDM managers are assigned both leave and timesheet approver roles and can therefore are assigned the timesheet menu and have the ability to submit and approve timesheets, even though this functionality is not in use by NDM |  | Check with Lyndsey if its possible to separate roles | In progress
46 | Process | LM | Holiday schemes | Need to override holiday scheme to employees moving to different department (with different T&Cs) part-way through the holiday year | Low | Need to establish a process to ensure we don’t lose track of the overrides in place. |  |  |  |  | 11/4/22: Overrides are in place for IT Services staff who have transferred into the Assurance Directorate. Simon suggests this needs an OSM request and a report for departments to run to keep track of any overrides. Also need review of how this fits into the employee lifecycle from a process and guidance perspective. We also need to decide who maintains the overrides - 1st line or security task. 4/5/22 Lois has added a line on overrides to the end of year checklist for departments to consider, however process needs agreeing internally.
47 | Process | LM | Secondments | Depts are currently having to do manual adjustments to balances for those on secondments. Need to agree process and then produce guidance on how balances should be assigned for those on secondments

## Drop downs
Category | Priority | Status
Policy | High | Not started
Guidance | Medium | In progress
Config | Low | Closed
Process
Reports
Access

## BC task list
Task | Which guide | Area | Assigned to | Priority | Progress | Refer to/Notes
Contact BO users to check whether they are active and update mailing list for contacting these stakeholders in future. Approx 50 responses so far. Chased the 21 outstanding replies on 11 May. 10 outstanding responses as of 17 May. Sent final reminder on 21 June to confirm role will be removed due to no response. |  | Comms | Lois | High | Complete | Now 48 subscribers (including our team) on mailing list - https://web.maillist.ox.ac.uk/ox/info/hris-absence-administrators File with list of absence admionistrators contacted (and their responses) saved on the Time Management Teams site (General/BAU Transition Pack/Absence admins list - role requirements for HC.xlsx)
Add Time Management system roles to the website and user access form (Want to end up with two roles, one for Timesheets and one for Leave roles (and no-one in BO).). |  | Website | Julie & Tonya | Medium | Not started
Ensure that all TIMDEP report descriptions include the line: Please note that only staff who hold a substantive appointment in the departments for which you have system access, will appear in your reports. |  | Website | Lois | High | Complete
FAQ needed on Staff Gateway re: 0.01p salary issue |  | Website | Lois | Medium | Complete | Email from Julie (6/4/22)
Produce end of year checklist for departments and HR Systems. Lois to share with Julie, tonya and Simon for input. |  | Training | Lois | Medium | Complete
Create onboarding checklist (incorporating items from Lessons Learnt doc and Lyndsey's CoreTime Timesheets rollout email of 24/2/22). Lois to send to Julie and share location. - Include how to add Time Manager role to future MSS roles - Make it clear helpdesk only take queries from HR staff. They should be first point of contact for ESS and MSS queries. Training to cover: How to claim holiday pay, Cancelling uploaded leave requests |  | Project | Julie & Lois | Low | In progress | Email from Julie (6/4/22)
Finalise document detailing Time Management roles. Note from JH - please can we add a note on here. I want to know who gets email notifications for leave and timesheets - when you have drafted please can we send to SB's team to confirm? |  | Website | Lois | Medium | In progress | 17/5/22: with Julie for review.
Update FAQs to clarify that users will receive an email and system notification when an action is required. These action notifications are: Line Managers: • When leave request has been submitted and requires approval • When an employee has self-certified a sickness absence record and they need to complete RTW details • When a timesheet has been submitted that requires their approval Employee: • When they need to self-certify a sickness absence Where you have multiple managers for a work group, do they all receive these emails? |  | Website | Lois | Low | Complete | https://unioxfordnexus.sharepoint.com/:x:/r/sites/UniversityAdministrationandServices-ITS816-CoreHRTimeManagem/Shared%20Documents/General/Business%20Analysis/Copy%20of%20CoreTime%20Notification%20settings%20v1.xlsx?d=wc80d103a037748b1819a89fc2269dfed&csf=1&web=1&e=kWuqpX
Update all HR Self-Service guidance webpages |  | Website | Julie & Lois | Medium | Complete
Add work email address requirement to FAQ on HRSS account setup |  | Website | Lois | Low | Complete
Review Tonys guidance re: annual leave balances and determine whats needed - ask Anna. To discuss in 4 May session | All | Guidance | Julie & Lois | Low | Not started | Email from Mandy (9 March)
Create guide on Work Groups - to include everything from HR Systems Briefing and clarity on Self-Service managers not in the same work group as their reports. | New | Guidance | Julie | Low | In progress
Save for later toggle | MSS TS Approver, NDM and other | Guidance | Julie | Low | Not started
Review all guidance not created by Julie | All | Guidance | Julie | Low | Not started
Add information on holiday balance calculations to website (visual in PDF). See email with doc from Lois | New | Guidance | Julie | Medium | Not started
Update both NDM and non-NDM guidance relating to visibility of co-workers and team calendar | NDM only | Guidance | Julie | Low | Not started | ID#35 on Outstanding Tasks for Time Management spreadsheet and Mandy's email to Lois 9 March
Need to update guidance to make clear that a reason code is mandatory and that the manager must always select a reason code of ‘Placeholder – employee to confirm’. This Guidance to be updated: https://staff.admin.ox.ac.uk/files/how-toguide-recordsicknessabsencemanagerpdf | MSS Record sickness absence - review NDM | Guidance | Julie | Medium | Not started | Simon's email (31 March)
Update Adjust a Leave Balance guide as per Mandy's email (11 April) | Adjust leave balance | Guidance | Julie | Medium | Not started
Update ESS guides for casuals. When entering timesheets for previous month it's confusing as current payroll period is this month - slightly confusing for them | ESS and MSS Add timesheet | Guidance | Julie | Medium | Not started
When managers login to MSS and hover over a submitted a timesheet it will say something similar to “Timesheet costed to XXX” but it will always say the default GL and not where it’s actually been costed to so it’s likely to cause some confusion and it’s something we will need to communicate up front for new roll outs. I guess we’ll end up with a FAQ and guide update. I’ll add to our master spreadsheet for now. Send email in first instance to Physics | MSS TS Approver, NDM and other | Guidance | Julie & Lois | Medium | Not started | FAQ, Guide and Onboarding comms
Can PERDEP16 report be amended to show all work group managers. Julie to raise ticket in OSM |  | Reports | Julie | Low | On Hold | OSM task raised and with Simon's team. This has already been requested and is on the POG list under item #228. It's been prioritised with a score of 22, which is medium priority. I think all the POG items for Workforce Management are going to be reviewed alongside your list and Mandy's list for candidates to be taken forward by the project team for a resolution, I'm not sure where this one will sit though. I don't have an easy solution, it's something we've always wanted to do but the solution to reporting on managers that we've been given by Access Group is the solution we have in place already, which only returns one manager per group, I have some vague ideas but there's nothing straight forward that can be done and will probably mean altering the security set up of everyone's reporting access to allow for reporting out of the security module, but even then it's ugly so there might be a better way. Anyway, we do have this logged so one way or another it will get looked at! Many thanks, Simon
Visibility of example timeline for deadlines and approvals - add to website (not critical until we onboard more depts) |  | Website | Lois | Low | Not started
Training helpdesk and Helen inc troubleshooting |  | Training | Julie | High | Complete
Ascertain what happens to Project Teams site. Transfer files from project Teams site elsewhere, if needed. |  | Admin | Lois | Low
Julie to send round list of issues/JIRAS to LM and ACW - then Jenny |  | Comms | Julie | High | Complete
Do we want to language pack 'Sign Off'? |  | Config | Julie | Medium | Not started
Set up end of annual leave year training for pilot depts on what they need to do. |  | Training | Julie | Medium | Not started
Move all training docs from SharePoint to TEAMS |  | Training | Julie | Low | Complete
Add all guides to Michelle's guides log |  | Guidance | Julie | Low | Not started
Physics meeting: Enhancement requests to report (email exchange between Tonya and Karla).Including: (1) Open access to report (2) Add Approved date (OSM with Athena) (3) Have two reports, one for identifying unapproved timesheets, one for reconciling |  | Guidance | Julie | High | In progress
Physics meeting: Create guidance document for depts needing to set up additional casuals (how to add required pay codes etc). Doc published online. Julie to share with Physics and Classics. |  | Config | Julie | Medium | In progress
Physics meeting: Chase issue where rejections are appearing in current month not the month they were rejected. With TAG. |  | Unknown | Julie | Medium | Not started | Email
Physics - Adding narratives |  | Comms | Lou | Low | On hold
Email pilot departments to request feedback |  | Comms | Rachel/Lou | Low | On hold
Email pilot departments to confirm that pilot project has closed and route for raising issues/requesting support from this point |  | Guidance | Julie | Low | On hold
When appropriate, add guides to what fix
Anna's items: